## Sheet1
Release Planning
Sprint No. | Phases | Week1 | Week2 | Week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14 | week15 | week16 | week17
Sprint 1 | Design | Week1: Apr 04-10
Sprint 1 | Development | Week2: Apr 11-17
Sprint 1 | Testing | Week3: Apr 18-24
Sprint 2 | Design | Week2: Apr 11-17
Sprint 2 | Development | Week3: Apr 18-24
Sprint 2 | Testing | Release Planning week4: Apr 25-30
Sprint 3 | Design | Week3: Apr 18-24
Sprint 3 | Development | Release Planning week4: Apr 25-30
Sprint 3 | Testing | Release Planning week5: May 1-7